## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | US1 | User | Register Myself Using Mail Id | I Can Receive A Confirmation/Verification Mail
1 | US2 | User | Receive A Confirmation Mail | I Can Access The Mycall System
1 | US3 | User | Login Into The System Using US ID or Mail Id And Password | I Can View/Edit My Profile
1 | US4 | User | View The Website | I Can See The Whole Website
1 | US5 | User | View The Adds | I Can Work According To The Time-Table
|  | User | Modify The Account Password | I Can Keep My Account Secure
|  | User | Give Feedback/Suggestions | The Way Of Working Of The MyCall Can Be Improved
|  | User | Discuss Among Other Users | I Can Share My Experience
|  | User | View My Indiscipline Activities | I Can Prevent The Mistakes
|  | User | View My Adds | I Can Keep A Check On My Activities
|  | User | View My Products | I Can Analyze My Performance
|  | User | View My Profile | I Can Manage My Attendance
|  | User | See The Product Status | I Can Pay The Fees On/Before Time
|  | User | See The No. of views on add | I Can Pay The Fine On Time
|  | User | See The Adds added By Me | I Can seeThe Adds On Website
|  | User | See My Product Information(If Used) | I Can Have Required Information
|  | User | View The List Of Products | I Can Participate In The listening
|  | User | View The List Of Categories | I Can Plan My Work
|  | User | Download the image of add | I Can Be download the image of Product
|  | User | Download the vedio of add | I Can Complete And Submit Them On Time
|  | DBA | Fire Insert Queries | I Can Insert New Records In The Database
|  | DBA | Fire Select Queries | I Can View The Records
|  | DBA | Fire Update Queries | I Can Keep The Database Updated
|  | DBA | Fire Delete Queries | I Can Remove Unwanted Or Faulty Data
|  | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use
|  | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More
|  | Admin | Login Into The System Using Mail Id And Password | I Can Access The MyCall
|  | Admin | Modify The Account Password | I Can Keep My Account Secure
|  | Admin | Finalize The Optional Subjects For Current Semester | Course Allotment Can Be Done
|  | Admin | Create User Accounts | Load Allotment Can Be Done
|  | Admin | Allot The type of add To The user | Time-Table Can Be Made
|  | Admin | View The timming of sale | I Can Monitor The Current Schedule
|  | Admin | Modify The Time of sale | The Schedule Can Be Modified Due To Changes
|  | Admin | View The Adds Of user | I Can Know The Product Strength on the MyCall
|  | Admin | View The Products Of User | I Can Know The Product Strength In The MyCall
|  | Admin | View The product list | I Can Keep A Check On The Product List .
|  | Admin | View The Report Of The user | I Can Monitor The Performance Of The User
|  | Admin | View Indiscipline Activities Of user | I Can Keep A Track Of Discipline
|  | Admin | View Indiscipline Activities Of editor | I Can Give Fair Marking In Editor Field
|  | Admin | View The List Of products or adds | I Can Plan Activities For The Celebration
|  | Admin | View The Participation Details Of Activities | Activeness Of The Makers of MyCall Can Be Seen
|  | Admin | Give Rewards To The User | Rewards Of Activities Can Be Given To user
|  | Admin | View User suggestion | The Quality Of Notes Can Be Reviewed
|  | Admin | Create ADD | I Can Pass On Important Information
|  | Admin | View Add | I Can Review Or Read New Notices
|  | Admin | Send call To user | They Can Be Informed For An Event
|  | Admin | Send report To user | They Can Be Informed about Their Adds
|  | Admin | Send Messages To user | They Can Be Given Important Notices/Updates
|  | Admin | View List Of Eligible Students For Placement | I Can Know The Number Of Eligible Students
|  | Author | Login Into The System Using Mail Id And Password | I Can View/Edit My Profile
|  | Author | Modify The Account Password | I Can Keep My Account Secure
|  | Author | View The Sale Time-Table | I Can Work According To The Time and Date
|  | Author | View The Advertisments Detalis | I Can Plan My Advertisments
|  | Author | Modify The Account Password | I Can Keep My Account Secure
|  | Author | View New Ads | I Can Review Or Read New Notices
|  | Author | Sending Information Through Emails | I Can Send Emails Regarding Important Informations
|  | Author | Assign Categories of Ads | I Can Assign categories To The Respective product
|  | Author | Can View The Details Of Ads | I Can Analyze The Details Of Product
|  | Author | Set The Criteria Of Perticular Ads | I Can Give criteria Of A product
|  | Author | View the Availabity of the product | I Can View The products in Stock
|  | Author | Assign Premium | I Can Assign Special category For The Particular Topic
|  | Author | Upload Pictures | I Can Upload various pictures
|  | Author | View The Sale Of Product | I Can View The Sale Of Product
|  | Author | Assign Description Of The Product | I Can Assign Description To The Product And Service
|  | Author | Provide Online Services | I Can Provide Sale of Product
|  | Author | Taking Online Feedback | I Can Take Online Feedbacks
|  | Author | Upolad Pictures | I Can Be Upload The Pictures
|  | Author | Upload Details | I Can Upload The Details of the Services
|  | Editor | Login Into The System Using Mail Id And Password | I Can Login Into The System
|  | Editor | Modify The Account Password | I Can Keep My Account Secure
|  | Editor | Manage The Tpo Activities | I Can Manage Tpo Activities
|  | Editor | Contact To The MyCall Representatives | I Can Contact To The MyCall Representatives
|  | Editor | Create A List Of Available Users | I Can Create A List Of Available Users
|  | Editor | Make Announcement Through Email | I Can Make Announcement Through Email
|  | Editor | Create A List Of Active Product of each category | I Can Create A List Of Active product In Each category
|  | Editor | Sending Information Through Emails | I Can Send Information Through Emails
|  | Editor | Display The Upcoming Products | I Can Display The Upcoming Products
|  | Editor | Set The Availability criteria Of Product | I Can Set The Criteria Of Product
|  | Editor | Manage The Time Schedule For Sale | I Can Manage The Time Schedule For Sale
|  | Editor | Select Different Responsibility For Respective users | I Can Select Manage The Time Schedule For Product
|  | Editor | View The Details Of All Products | I Can View All The Details Of Products
|  | Editor | Prepare Account For All Eligible users | I Can Prepare Account For All Eligible Users
|  | Editor | Assign Duties To categorised users | I Can Assign Duties To categoriesed Users
|  | Editor | Update Time duration For Product Sale | I Can Update Time Duration For Product Sale
|  | Editor | Access To All Information Of Products | I Can Access The Information Of Products
|  | Editor | Display Total Selections of Products | I Can Display Total Selections of Products
|  | Editor | Manage All Statistics And Data About Product Sale | I Can Manage All Statistics And Data About Product Sales
|  | Editor | Review And Feedback From User By Email | I Can Review And Feedback From User By Email
|  | Editor | Login Into The System Using Mail Id And Password | I Can Login Into The System
|  | Contributor | Modify The Account Password | I Can Keep My Account Secure
|  | Contributor | Manage The Customer Activities | I Can Manage customers Activities
|  | Contributor | Maintain Data Of All Users | I Can Maintain Data Of All Users
|  | Contributor | Maintain Data Of All customers | I Can Maintain Data Of All Customers
|  | Contributor | Assign Duties To All users | I Can Assign Duties To All users
|  | Contributor | Manage The Entries Of Product As Per Time Schedule | I Can Manage The Entries Of Product As Per Time Schedule
|  | Contributor | Display Contact Details Of Each Driver | I Can Display Contcat Details Of Each Driver
|  | Contributor | Provding Id No To The Students To Avail Transport Service | I Can Provide Id No To Students To Avail Transport Service
|  | Contributor | Display And Set The Fee Structure As Per Km | I Can Display And Set The Fee Structure As Per Km
|  | Contributor | Make Proper Contacts To Update Any Change | I Can Make Proper Contacts To Update Any Change
|  | Contributor | Acces To Whole Information About Pickup Points | I Can Access The Details Of All Pickup Points
|  | Contributor | Update Time And Place Detail For A Bus | I Can Update Time And Place Detail For A Bus
|  | Contributor | Provide Separate Buses For Faculties And Support Staff | I Can Provide Separate Buses For Faculties And Other Staff
|  | Contributor | Display The Route Info. For Each Bus | I Can Display The Route Info For Each Bus
|  | Contributor | View The List Of Holidays In A Calender Year | View The Details Of Holidays In A Calender Year
|  | Contributor | Manage Alternate Route In Case Of Traffic | I Can Manage Alternate Route In Case Of Traffic
|  | Contributor | Share Contact Info Of Incharge Of The Campus Transport | I Can Share The Contact Info Of Incharge
|  | Contributor | Assign Shift As Per Requirement | I Can Assign Shift As Per Requirement
|  | Contributor | Feedback From Students And Faculties | I Can Feedback From Students And Faculties
|  | Contributor | Maintain The Student Indiscipline Activity Details | I Can Give The Discipline Marks Accordingly
|  | TUTOR | Maintain The Student Extra Curricular Activity Details | I Can Give Bonus Attendance And Marks Accordingly
|  | TUTOR | Contact Parents | I Can Tell Them The Student Performance
|  | TUTOR | View The Debar List | I Can Let Their Parents Know
|  | TUTOR | Create New Time Table | Students & Faculty Would Know The Schedule
|  | Timetable CO. | Modify The Time Table | Modification Can Be Done
|  | Timetable CO. | Allocate The Subjects To Faculties | Faculty Will Come To Know What To Teach
|  | Timetable CO. | Login Into The System Using Poornima Mail Id And Password | I Can Login Into The System
|  | Librarian | Modify The Account Password | I Can Keep My Account Secure
|  | Librarian | I Want To Insert Book Details | So That Books Information Remain In Database
|  | Librarian | Issue Books | It Is Provided To Students
|  | Librarian | Request To Purchase Books For Library | To Fulfill The Requirements Of Students
|  | Librarian | Request To Purchase Available Resources | To Fulfill The Requirements Of Students
|  | Librarian | Manage The Fine As Per Issued Books | Total Fine Will Be Deducted From Caution Money At The End
|  | Librarian | Make Available Books | To Fulfill The Needs Of Students
|  | Librarian | Makes Available Internet Facility | To Fulfill The Needs Of Students
|  | Librarian | Make Available New Edition Books | Students Are Aware Of Updation In The Book
|  | Librarian | Manage The Copy Of Non-Issue And Issued Books | Books Are Kept Accordingly
|  | Librarian | Manage Novel | Students Get The Knowledge As Per Their Interest
|  | Librarian | Manage Magzines | Students Get The Knowledge As Per Their Interest
|  | Librarian | Manage Old Question Papers Of Midterms And Rtu | Students Get In Touch With The Subject
|  | Librarian | Sms Facility When Due Books | Students Are Aware To Submit The Issued Book On Time
|  | Librarian | Book Availability Alert When A Books Available | Issued Book Is Make Available For Those Who Need It Most
|  | Librarian | New Books ,Magzine, Novel Arrival Alert | Students Get To Know About New Arrivals In Library
|  | Librarian | Book Reference Disk (Cd/Dvd) Content | Students Will Get More Information Related To Subject
|  | Librarian | Manage Entry Of Students | So That Library Record Can Be Maintained
|  | Librarian | Research Paper Management(Content) | So That Students Get Relevant Information
|  | Librarian | Jobs Alert | So That Students Are Aware Of New Job Openings
|  | Librarian | Open Book Test | Students Are Aware About The Topics Of Standard Books
|  | Librarian | Book Review Competition | So That Student Will Put Their Reviews Infront Of Others
|  | Librarian | Project Review Reports Important Samples | It Will Be Available For Students Who Need It Most
|  | Librarian | Manages Different Sections(Reading,Refer,E-Lib) | Easily Available For Everyone As Per Their Need
|  | Librarian | Library Review And Book Review By Users | Share the review with others
|  | Librarian | Login Into The System Using Poornima Mail Id And Password | I Can Login Into The System
|  | Executive | Modify The Account Password | I Can Keep My Account Secure
|  | Executive | Insert Fee Details | Student Record Related To Fee Is Updated
|  | Executive | Update Hostel Fees | Hostel Irecord Is Up To Date
|  | Executive | Put Fine For Late Fee | Student Are Aware To Submit Fee On Time
|  | Executive | Contact Student | Any Issue Related To Student Is Solved And Informed
|  | Executive | Put Fine For Indiscipline Activity | Indiscipline Activity Are To Be Minimised
|  | Executive | Update The Format Of Fees Receipt | Format Should Be Clear And Conscise
|  | Executive | Contact Director | Overall Activity Report Is Provided To Them
|  | Executive | Monitor Bank Transaction Related To Fee | Fees Updation Procedure Should Be Consistent
|  | Executive | Handle University Exam Form Submission | Exam Fees Are Together Submitted To University
|  | Executive | Handle Transport Fees | Transport Is Make Available To Respective Students
|  | Executive | Handle Money Issues | Supervision Is There
|  | Executive | Manage Technical Staff | Student Contact Directly To Them
|  | Executive | Manage Report As Per Fees To Be Submitted To Head | Director Knows About What Is Happening
|  | Executive | Manage The Faculty Transport Fees | A Specialised Fee For Them
|  | Executive | Manage The Interview Session For New Faculty | New People Get Their Appointment As Per Their Schedule
|  | Executive | Monitor Transport Officer | Transport Related Issues Are To Be Solved
|  | Executive | Manage Salary Of Faculties | The Salary Is Provided To Them On Time
|  | Executive | Manage Salary Of Technical Consultants | The Salary Is Provided To Them On Time
|  | Executive | Manage Convention Centre Booking | Any Competion As Well As Activity Is Conducted
|  | Executive | Manage Task Related To Money | Money Should Be Utilized And Not Wasted
|  | Executive | Monitor Server Control Of College | Lab Work Should Be Flexible And Effective
|  | Director | Login Into The System Using Poornima Mail Id And Password | I Can Login Into The System
|  | Director | Modify The Account Password | I Can Keep My Account Secure
|  | Director | Manage The Administration | To Monitor The Effective Supervision
|  | Director | Make Rules | To Assign Equal Responsibility To Everyone
|  | Director | Manage Branches | Workflow Should Be Monitored
|  | Director | Assign Responsibilities To Hod'S,Proctor Etc. | They Will Work According To Their Responsibility
|  | Director | Take Interview Of New Faculties | Faculties With Good Knowledge Will Be Available
|  | Director | Assign Tasks To Campus Director | Hods,Proctor Report To Them And Not Director Everytime
|  | Director | Manage The Placement Activity | Reputed Companies Are Come For Placement
|  | Director | Decide To Allow Activity Conduction As Per Norms | Students Get To Know About Other Things
|  | Director | Monitor Fee Structure | As Per Resources Available Students Get All They Basic Needs
|  | Director | Monitor Teaching As Per Requirement And Rules | Effective Teaching Is Conducted
|  | Director | Monitor Faculty Report And Work | Faculties Are Strict To Follow Norms And Rules
|  | Director | Monitors Admission Norms | Student Admissions Are Increased In College
|  | Director | Impliment Effective Environment All Over | Peaceful Environment And Effective Use Of Resources Are Accomplished
|  | Director | Allow Funding As Per The Resources Need | Resources As Per The Requirement Make Available
|  | Director | Manage Overall Functioning | To Promote Effective And Robust Teaching
|  | Director | Monitors Exam Cell And Their Functioning | Exams Are Conducted In Proper Manner
|  | Director | Monitors The Transport Safety For Day Scholars | Travelling Should Be Safe And Secure
|  | Director | Allow Conference Activity In College | To Promote Knowledge Sharing
|  | Director | Allow Sports Activity As Per Students Need | To Promote Co-Curricular Activities In College
|  | Director | Allow Partnership With Colleges Around | Inter College Activities Are Organized
|  | Director | Monitors And Removes Indicipline Activity In College | Effective Discipline Is Maintained
|  | TA | Login Into The System Using Poornima Mail Id And Password | I Can Login Into The System Using Poornima Mail Id And Password
|  | TA | Modify The Account Password | I Can Keep My Account Secure
|  | TA | Request Complaint Of Students | Students Indiscipined Activity Can Be Recorded
|  | TA | Request For Lab Resources to HOD | The Resources In The Lab Can Be Maintained
|  | TA | View The Requirement Of The Labs | I Can Prepare The Resources
|  | Student | Add Hobbies | I can make my Resume Easily

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <MyCall>
SB3/US1 | Design the LogIn Page | SB3/D1/T1 | Design the interface of LogIn page | SS
|  | SB3/D1/T2 | Connect the page with Social Media pages | SS
|  | SB3/D1/T3 | Design the user dashboard page | SS+SO
SB3/US2 | Design the SignUp Page | SB3/D2/T1 | Design the User interfae of SignUp page | SS+SR
|  | SB3/D2/T2 | Join the Signup page with Social media | SO+SR
|  | SB3/D2/T3 | Connect SignUp page with the Server | SO
|  | SB3/D2/T4 | Join UserId with the E-mail | SR
|  | SB3/D2/T5 | Design the user dashboard page | SS+SR+SO
SB3/US3 | Design Forgot Password Section | SB3/D3/T1 | Design the interface of forgot password page | SO
|  | SB3/D3/T2 | Join userid with gmail to verify | SR
|  | SB3/D3/T3 | Verify password through gmail | SS
|  | SB3/D3/T4 | Inform user about change password | SS
SB3/US4 | Design the Home Page | SB3/D4/T1 | Design the interface of Home page | SS+SR
|  | SB3/D4/T2 | Design the interface of Contents | SO+SS
|  | SB3/D4/T3 | Design Advertisments Section | SO+SR
|  | SB3/D4/T4 | Make Page Seprately of each Advertisments | SS
SB3/US5 | Design Advertisments panel | SB3/D5/T1 | Make individual page of each advertisments | SS+SO+SR
|  | SB3/D5/T2 | Write all the details of the product | SS
|  | SB3/D5/T3 | Take user's feedbacks | SO
|  | SB3/D5/T4 | Notify everything to Admin | SR
SB3/US6 | Design Product Section | SB3/D6/T1 | Design Search pannel including categorywise | SS+SO+SR
|  | SB3/D6/T2 | Search services areawise | SR
|  | SB3/D6/T3 | Show locations of services | SR
|  | SB3/D6/T4 | Share feedback to admin | SO
|  | SB3/D6/T5 | Add Security check section before purchasing | SS+SR
SB3/US7 | Live the website | SB3/D7/T1 | Get a domain name for website | SO
|  | SB3/D7/T2 | Get a hosting space for website | SO+SS
|  | SB3/D7/T3 | Upload the data on the server | SS+SR
|  | SB3/D7/T4 | All data is live uploaded and check the connection of pages | SO+SR
SB3/US8 | Maintain | SB3/D8/T1 | Connection with Server | SS
|  | SB3/D8/T2 | Upload the latest data on the Server | SS
|  | SB3/D8/T3 | Backup of all Data | SR
|  | SB3/D8/T4 | Offline backup | SO

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Design the LogIn Page | Design the interface of LogIn page | SS
|  | Connect the page with Social Media pages | SS
|  | Design the user dashboard page | SS+SO
2 | Design the SignUp Page | Design the User interfae of SignUp page | SS+SR
|  | Join the Signup page with Social media | SO+SR
|  | Connect SignUp page with the Server | SO+SR
|  | Join UserId with the E-mail | SO
3 | Design Forgot Password Section | Design the interface of forgot password page | SO
|  | Join userid with gmail to verify | SR
|  | Verify password through gmail | SS
4 | Design the Home Page | Design the interface of Home page | SO+SR+SS
|  | Design the interface of Contents | SO+SS
|  | Design Advertisments Section | SO+SR
|  | Make Page Seprately of each Advertisments | SR+SS
| Design Advertisments panel | Make individual page of each advertisments | SS+SO+SR
|  | Write all the details of the product | SS
|  | Take user's feedbacks | SO
|  | Notify everything to Admin | SR
5 | Design Product Section | Design Search pannel including categorywise | SR
|  | Search services areawise | SR
|  | Show locations of services | SO
|  | Share feedback to admin | SR
6 | Live the website | Get a domain name for website | SO
|  | Get a hosting space for website | SS
|  | Upload the data on the server | SR+SS
|  | All data is live uploaded and check the connection of pages | SO+SS
| SS | Shashank Sharma
| SR | Shaurya Ranjan
| SO | Sourav Choudhary
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 20 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <MyCall>
SB1/US1 | Register Myself Using Mail Id | SB1/D1/T1 | User Interface for Registration
|  | SB1/D1/T2 | Validation of the details
|  | SB1/D1/T3 | Connect Registration page with the server
|  | SB1/D1/T4 | Upload uesr details to server and store in database
|  | SB1/D1/T5 | Inform User if successfully register
|  | SB1/D1/T6 | Send Mail to user on successfully register
SB1/US2 | Login into Website | SB1/D2/T1 | User Interface for Registration
|  | SB1/D2/T2 | Validation of the details
|  | SB1/D2/T3 | Connect Registration page with the server
|  | SB1/D2/T4 | Connect Registration page with the server
|  | SB1/D2/T5 | Send Mail to user on successfully register
SB1/US3 | Register Editor Using Mail Id | SB1/D3/T1 | User Interface for Registration
|  | SB1/D3/T2 | Validation of the details
|  | SB1/D3/T3 | Connect Registration page with the server
|  | SB1/D3/T4 | Send Mail to user on successfully register
SB1/US6 | Register Myself as Subscriber | SB1/D4/T1 | User Interface for Registration
|  | SB1/D4/T2 | Validation of the details
|  | SB1/D4/T3 | Connect Registration page with the server
|  | SB1/D4/T4 | Upload uesr details to server and store in database
|  | SB1/D4/T5 | Send Mail to user on successfully register
SB1/US7 | Validation of login | SB1/D5/T1 | Validation of the details
|  | SB1/D5/T2 | Connect Registration page with the server
|  | SB1/D5/T3 | Upload uesr details to server and store in database
|  | SB1/D5/T4 | Send Mail to user on successfully register
SB1/US27 |  | SB1/D6/T1
SB1/D6/T2
SB1/D6/T3
SB1/D6/T4
SB1/D6/T5
SB1/US27 |  | SB1/D7/T2
SB1/D7/T3
SB1/D7/T4
SB1/D7/T5
SB1/US150 |  | SB1/D8/T1
SB1/D8/T2
SB1/D8/T3
SB1/D8/T4
SB1/US28 |  | SB1/D9/T1
SB1/D9/T2
SB1/D9/T3
SB1/D9/T4
SB1/D9/T5
SB1/US50 |  | SB1/D10/T1
SB1/D10/T2
SB1/D10/T3
SB1/D10/T4
SB1/D10/T5
SB1/US53 |  | SB1/D11/T2
SB1/D11/T3
SB1/D11/T4
SB1/D11/T5
SB1/US55 |  | SB1/D12/T1
SB1/D12/T2
SB1/D12/T3
SB1/D12/T4
SB1/US51 |  | SB1/D13/T1
SB1/D13/T2
SB1/D13/T3
SB1/D13/T4
SB1/D13/T5
SB1/US70 |  | SB1/D14/T1
SB1/D14/T2
SB1/D14/T3
SB1/D14/T4
SB1/D14/T5
SB1/US71 |  | SB1/D15/T2
SB1/D15/T3
SB1/D15/T4
SB1/D15/T5
SB1/US72 |  | SB1/D16/T1
SB1/D16/T2
SB1/D16/T3
SB1/D16/T4

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <MyCall>
SB3/US1 | Join Database | SB3/D1/T1 | Create Database of Website | SS
|  | SB3/D1/T2 | Create Attributes of Databse | SR
|  | SB3/D1/T3 | Combine database with the website. | SO
SB3/US2 | Store in Database | SB3/D2/T1 | Store Signup details in Databse | SR+SS
|  | SB3/D2/T2 | Insert Login Details | SO
|  | SB3/D2/T3 | Insert Products Details | SS+SO
|  | SB3/D2/T4 | Insert Services Data | SO
|  | SB3/D2/T5 | Store all details in Database | SR+SO
SB3/US3 | Retrive Data | SB3/D3/T1 | Retrive data from Database for logIn | SO+SS
|  | SB3/D3/T2 | Show all data of Product or services | SS+SR
|  | SB3/D3/T3 | Keep record of all the data with timestrap | SR+SO
|  | SB3/D3/T4 | Receive the latest data from the Server | SR
SB3/US4 | BackUp/Maintain | SB3/D4/T1 | Take backup of whole database | SS
|  | SB3/D4/T2 | Import all data of Website | SR
|  | SB3/D4/T3 | Keep an Offline SQL backup file | SO
|  | SB3/D4/T4 | Update the backup file | SO
|  | SB3/D4/T5 | Maintain the new updates | SS
SB3/US5 | Content | SB3/D5/T1 | Insert Home Page Content | SS
|  | SB3/D5/T2 | Insert Categories Data | SR
|  | SB3/D5/T3 | Insert Adertisments and their data | SO
|  | SB3/D5/T4 | Detailed Advertisments | SS+SO

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Join Database | Create Database of Website | SS+SO
|  | Create Attributes of Databse | SR
|  | Combine database with the website. | SR+SO
2 | Store in Database | Store Signup details in Databse | SS+SR
|  | Insert Login Details | SS+SO
|  | Insert Products Details | SO
|  | Insert Services Data | SO
3 | Retrive Data | Retrive data from Database for logIn | SS
|  | Show all data of Product or services | SR
|  | Keep record of all the data with timestrap | SR+SO
|  | Receive the latest data from the Server | SS
4 | BackUp/Maintain | Take backup of whole database | SS
|  | Import all data of Website | SR+SO
|  | Keep an Offline SQL backup file | SO+SS
|  | Update the backup file | SO
| SS | Shashank Sharma
| SR | Shaurya Ranjan
| SO | Sourav Choudhary
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 80 | 0 | Tasks
2018-10-18 | 80 | 0
2018-10-20 | 110 | 60
2018-10-21 | 90 | 75
2018-10-22 | 120 | 120
2018-10-23 | 50 | 0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>
| Add Department | SB2/D1/T1 | Designing the GUI | SS
|  | SB2/D1/T2 | Connection with database to fetch the data | RA
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TA into the application(using poornima email account) | SB2/D2/T1 | Designing of GUI | PB
|  | SB2/D2/T2 | Validating user input at client level | RM
|  | SB2/D2/T3 | Validating user input at server level | SP
|  | SB2/D2/T4 | Connection with Database to insert the record. | RA
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TA Receiving Confirmation Email | SB2/D3/T1 | Designing of Email(to be send) | PB
|  | SB2/D3/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D3/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D3/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TO into the application(using poornima email account) | SB2/D4/T1 | Designing of GUI | PB
|  | SB2/D4/T2 | Validating user input at client level | RM
|  | SB2/D4/T3 | Validating user input at server level | SP
|  | SB2/D4/T4 | Connection with Database to insert the record. | RA
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TO Receiving Confirmation Email | SB2/D5/T1 | Designing of Email(to be send) | PB
|  | SB2/D5/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D5/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D5/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Add Subject | SB2/D6/T1 | Designing of GUI | PB
|  | SB2/D6/T2 | Validating user input at client level | RM
|  | SB2/D6/T3 | Validating user input at server level | SP
|  | SB2/D6/T4 | Connection with Database to insert the record. | RA
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register Timetable Co-ordinator into the application | SB2/D7/T1 | Designing of GUI | PB
|  | SB2/D7/T2 | Validating user input at client level | RM
|  | SB2/D7/T3 | Validating user input at server level | SP
|  | SB2/D7/T4 | Connection with Database to insert the record. | RA
|  | SB2/D7/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Timetable Co-ordinator Receiving Confirmation Email | SB2/D8/T1 | Designing of Email(to be send) | PB
|  | SB2/D8/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D8/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D8/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB4/US5 | Testing | SB4/D5/T1 | Test the working of Website | SS
|  | SB4/D5/T2 | Connection of webpages | SO
|  | SB4/D5/T3 | Working of each fields | SR
|  | SB4/D5/T4 | Insert and Retrive of all Data in Webpages | SR+SO

## SB Hours 04
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
5 | Testing | Test the working of Website | SS+SR+SO
|  | Connection of webpages | SS
|  | Working of each fields | SR
|  | Insert and Retrive of all Data in Webpages | SO
PM
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 100 | 80
2019-01-13 | 125 | 90
2019-01-14 | 150 | 70
2019-01-15 | 0 | 0
0
Days