## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | US1 | User | Register Myself Using Mail Id | I Can Receive A Confirmation/Verification Mail
2 | US2 | User | Receive A Confirmation Mail | I Can Access The Mycall System
3 | US3 | User | Login Into The System Using US ID or Mail Id And Password | I Can View/Edit My Profile
4 | US4 | User | View The Website | I Can See The Whole Website
5 | US5 | User | View The Adds | I Can Work According To The Time-Table
6 |  | User | Modify The Account Password | I Can Keep My Account Secure
7 |  | User | Give Feedback/Suggestions | The Way Of Working Of The MyCall Can Be Improved
8 |  | User | Discuss Among Other Users | I Can Share My Experience
9 |  | User | View My Indiscipline Activities | I Can Prevent The Mistakes
10 |  | User | View My Adds | I Can Keep A Check On My Activities
11 |  | User | View My Products | I Can Analyze My Performance
12 |  | User | View My Profile | I Can Manage My Attendance
13 |  | User | See The Product Status | I Can Pay The Fees On/Before Time
14 |  | User | See The No. of views on add | I Can Pay The Fine On Time
15 |  | User | See The Adds added By Me | I Can seeThe Adds On Website
16 |  | User | See My Product Information(If Used) | I Can Have Required Information
17 |  | User | View The List Of Products | I Can Participate In The listening
18 |  | User | View The List Of Categories | I Can Plan My Work
19 |  | User | Download the image of add | I Can Be download the image of Product
20 |  | User | Download the vedio of add | I Can Complete And Submit Them On Time
21 |  | DBA | Fire Insert Queries | I Can Insert New Records In The Database
22 |  | DBA | Fire Select Queries | I Can View The Records
23 |  | DBA | Fire Update Queries | I Can Keep The Database Updated
24 |  | DBA | Fire Delete Queries | I Can Remove Unwanted Or Faulty Data
25 |  | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use
26 |  | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More
27 |  | Admin | Login Into The System Using Mail Id And Password | I Can Access The MyCall
28 |  | Admin | Modify The Account Password | I Can Keep My Account Secure
29 |  | Admin | Finalize The Optional Subjects For Current Semester | Course Allotment Can Be Done
30 |  | Admin | Create User Accounts | Load Allotment Can Be Done
31 |  | Admin | Allot The type of add To The user | Time-Table Can Be Made
32 |  | Admin | View The timming of sale | I Can Monitor The Current Schedule
33 |  | Admin | Modify The Time of sale | The Schedule Can Be Modified Due To Changes
34 |  | Admin | View The Adds Of user | I Can Know The Product Strength on the MyCall
35 |  | Admin | View The Products Of User | I Can Know The Product Strength In The MyCall
36 |  | Admin | View The product list | I Can Keep A Check On The Product List .
37 |  | Admin | View The Report Of The user | I Can Monitor The Performance Of The User
38 |  | Admin | View Indiscipline Activities Of user | I Can Keep A Track Of Discipline
39 |  | Admin | View Indiscipline Activities Of editor | I Can Give Fair Marking In Editor Field
40 |  | Admin | View The List Of products or adds | I Can Plan Activities For The Celebration
41 |  | Admin | View The Participation Details Of Activities | Activeness Of The Makers of MyCall Can Be Seen
42 |  | Admin | Give Rewards To The User | Rewards Of Activities Can Be Given To user
43 |  | Admin | View User suggestion | The Quality Of Notes Can Be Reviewed
44 |  | Admin | Create ADD | I Can Pass On Important Information
45 |  | Admin | View Add | I Can Review Or Read New Notices
46 |  | Admin | Send call To user | They Can Be Informed For An Event
47 |  | Admin | Send report To user | They Can Be Informed about Their Adds
48 |  | Admin | Send Messages To user | They Can Be Given Important Notices/Updates
49 |  | Admin | View List Of Eligible Students For Placement | I Can Know The Number Of Eligible Students
50 |  | Author | Login Into The System Using Mail Id And Password | I Can View/Edit My Profile
51 |  | Author | Modify The Account Password | I Can Keep My Account Secure
52 |  | Author | View The Sale Time-Table | I Can Work According To The Time and Date
53 |  | Author | View The Advertisments Detalis | I Can Plan My Advertisments
54 |  | Author | Modify The Account Password | I Can Keep My Account Secure
55 |  | Author | View New Ads | I Can Review Or Read New Notices
56 |  | Author | Sending Information Through Emails | I Can Send Emails Regarding Important Informations
57 |  | Author | Assign Categories of Ads | I Can Assign categories To The Respective product
58 |  | Author | Can View The Details Of Ads | I Can Analyze The Details Of Product
59 |  | Author | Set The Criteria Of Perticular Ads | I Can Give criteria Of A product
60 |  | Author | View the Availabity of the product | I Can View The products in Stock
61 |  | Author | Assign Premium | I Can Assign Special category For The Particular Topic
62 |  | Author | Upload Pictures | I Can Upload various pictures
63 |  | Author | View The Sale Of Product | I Can View The Sale Of Product
64 |  | Author | Assign Description Of The Product | I Can Assign Description To The Product And Service
65 |  | Author | Provide Online Services | I Can Provide Sale of Product
66 |  | Author | Taking Online Feedback | I Can Take Online Feedbacks
67 |  | Author | Upolad Pictures | I Can Be Upload The Pictures
68 |  | Author | Upload Details | I Can Upload The Details of the Services
69 |  | Editor | Login Into The System Using Mail Id And Password | I Can Login Into The System
70 |  | Editor | Modify The Account Password | I Can Keep My Account Secure
71 |  | Editor | Manage The Tpo Activities | I Can Manage Tpo Activities
72 |  | Editor | Connect Pages | I Can Connect pages like login & Signup pages
73 |  | Editor | Create A List Of Available Users | I Can Create A List Of Available Users
74 |  | Editor | Make Announcement Through Email | I Can Make Announcement Through Email
75 |  | Editor | Create A List Of Active Product of each category | I Can Create A List Of Active product In Each category
76 |  | Editor | Sending Information Through Emails | I Can Send Information Through Emails
77 |  | Editor | Display The Upcoming Products | I Can Display The Upcoming Products
78 |  | Editor | Set The Availability criteria Of Product | I Can Set The Criteria Of Product
79 |  | Editor | Manage The Time Schedule For Sale | I Can Manage The Time Schedule For Sale
80 |  | Editor | Select Different Responsibility For Respective users | I Can Select Manage The Time Schedule For Product
81 |  | Editor | View The Details Of All Products | I Can View All The Details Of Products
82 |  | Editor | Prepare Account For All Eligible users | I Can Prepare Account For All Eligible Users
83 |  | Editor | Assign Duties To categorised users | I Can Assign Duties To categoriesed Users
84 |  | Editor | Update Time duration For Product Sale | I Can Update Time Duration For Product Sale
85 |  | Editor | Access To All Information Of Products | I Can Access The Information Of Products
86 |  | Editor | Display Total Selections of Products | I Can Display Total Selections of Products
87 |  | Editor | Manage All Statistics And Data About Product Sale | I Can Manage All Statistics And Data About Product Sales
88 |  | Editor | Review And Feedback From User By Email | I Can Review And Feedback From User By Email
89 |  | Editor | Login Into The System Using Mail Id And Password | I Can Login Into The System
90 |  | Contributor | Modify The Account Password | I Can Keep My Account Secure
91 |  | Contributor | Manage The Customer Activities | I Can Manage customers Activities
92 |  | Contributor | Maintain Data Of All Users | I Can Maintain Data Of All Users
93 |  | Contributor | Maintain Data Of All customers | I Can Maintain Data Of All Customers
94 |  | Contributor | Assign Duties To All users | I Can Assign Duties To All users
95 |  | Contributor | Manage The Entries Of Product As Per Time Schedule | I Can Manage The Entries Of Product As Per Time Schedule
96 |  | Contributor | Display Contact Details Of Each Driver | I Can Display Contcat Details Of Each Driver
97 |  | Contributor | Provding Id No To The Students To Avail Transport Service | I Can Provide Id No To Students To Avail Transport Service
98 |  | Contributor | Display And Set The Fee Structure As Per Km | I Can Display And Set The Fee Structure As Per Km
99 |  | Contributor | Make Proper Contacts To Update Any Change | I Can Make Proper Contacts To Update Any Change
100 |  | Contributor | Acces To Whole Information About Pickup Points | I Can Access The Details Of All Pickup Points
101 |  | Contributor | Update Time And Place Detail For A Bus | I Can Update Time And Place Detail For A Bus
102 |  | Contributor | Provide Separate Buses For Faculties And Support Staff | I Can Provide Separate Buses For Faculties And Other Staff
103 |  | Contributor | Display The Route Info. For Each Bus | I Can Display The Route Info For Each Bus
104 |  | Contributor | View The List Of Holidays In A Calender Year | View The Details Of Holidays In A Calender Year
105 |  | Contributor | Manage Alternate Route In Case Of Traffic | I Can Manage Alternate Route In Case Of Traffic
106 |  | Contributor | Share Contact Info Of Incharge Of The Campus Transport | I Can Share The Contact Info Of Incharge
107 |  | Contributor | Assign Shift As Per Requirement | I Can Assign Shift As Per Requirement
108 |  | Contributor | Feedback From Students And Faculties | I Can Feedback From Students And Faculties
109 |  | Contributor | Maintain The Student Indiscipline Activity Details | I Can Give The Discipline Marks Accordingly

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <MyCall>
SB1/US1 | Register Myself Using Mail Id | SB1/D1/T1 | User Interface for Registration | SO | INPROGRESS
|  | SB1/D1/T2 | Validation of the details | SR | INPROGRESS
|  | SB1/D1/T3 | Connect Registration page with the server | SS | INPROGRESS
|  | SB1/D1/T4 | Upload uesr details to server and store in database | SR+SO | INPROGRESS
|  | SB1/D1/T5 | Inform User if successfully register | SS+SO | INPROGRESS
|  | SB1/D1/T6 | Send Mail to user on successfully register | SO | INPROGRESS
SB1/US2 | Design Front end Pages | SB1/D2/T1 | User Interface for Registration | SS | INPROGRESS
|  | SB1/D2/T2 | Validation of the details | SR | INPROGRESS
|  | SB1/D2/T3 | User Interface for Login | SO | INPROGRESS
|  | SB1/D2/T4 | User Interface for Home Page | SR+SS | INPROGRESS
|  | SB1/D2/T5 | User Interface for Help And Support | SR | INPROGRESS
SB1/US3 | Register Editor Using Mail Id | SB1/D3/T1 | User Interface for Registration | SS | INPROGRESS
|  | SB1/D3/T2 | Validation of the details | SR+SS | INPROGRESS
|  | SB1/D3/T3 | Check confirmation mail | SO | INPROGRESS
|  | SB1/D3/T4 | Send Mail to user on successfully register | SR+SS | INPROGRESS
SB1/US6 | Integrate all the code &files , images,etc | SB1/D4/T1 | User Interface for Registration | SS+SO | INPROGRESS
|  | SB1/D4/T2 | Validation of the details | SS | INPROGRESS
|  | SB1/D4/T3 | Collect the images of themes of mycall | SR | INPROGRESS
|  | SB1/D4/T4 | check the size of images | SO | INPROGRESS
|  | SB1/D4/T5 | Check the code format ,image formate before uploading on server | SS+SR | INPROGRESS
SB1/US7 | Testing | SB1/D5/T1 | Editor will check the code on localhost and then on server | SO | INPROGRESS
|  | SB1/D5/T2 | Create the user as per admin permission | SS | INPROGRESS
|  | SB1/D5/T3 | Upload uesr details to server and store in database | SO | INPROGRESS
|  | SB1/D5/T4 | Send Mail to user on successfully register | SR | INPROGRESS
SB1/US27 | Live(For testing Purpose)on Server | SB1/D6/T1 | Admin Will Buy the needed required services for live the project | SS | INPROGRESS
|  | SB1/D6/T2 | Admin will Buy the services for hosting and domain | SR+SS | INPROGRESS
|  | SB1/D6/T3 | admin will check the security of website | SO+SS | INPROGRESS
|  | SB1/D6/T4 | admin will buy security services for its website | SR+SS | INPROGRESS
|  | SB1/D6/T5 | Admin and editor will live the project for testing on their website | SR | INPROGRESS
SB1/US27 | Check the database | SB1/D7/T2 | DBA will check the database after live the project on server | SS+SR | INPROGRESS
|  | SB1/D7/T3 | DBA will fire the queries for various purpose | SS | INPROGRESS
|  | SB1/D7/T4 | editor will check the code on server | SO | INPROGRESS
|  | SB1/D7/T5 | Admin & editor will check the project for testing on their website | SR | INPROGRESS

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Register Myself Using Mail Id | User Interface for Registration | SS
|  | Validation of the details | SR
|  | Connect Registration page with the server | SO
|  | Send Mail to user on successfully register | SO
2 | Design Front end Pages | User Interface for Registration | SS+SR
|  | User Interface for Login | SO+SR
|  | User Interface for Home Page | SS+SR
|  | User Interface for Help And Support | SO+SR
3 | Register Editor Using Mail Id | Check confirmation mail | SR
|  | Send Mail to user on successfully register | SO
4 | Integrate all the code & files,images,etc | Collect the images of themes of mycall | SO
|  | check the size of images | SO
|  | Check the code format ,image formate before uploading on server | SR |  |  | 0
0
5 | Testing | Editor will check the code on localhost and then on server | SS |  |  | 0
|  | Create the user as per admin permission | SS+SO |  |  | 0
|  | Upload uesr details to server and store in database | SS+SR
|  | Send Mail to user on successfully register | SO+SR
6 | Live(For testing Purpose)on Server | Admin Will Buy the needed required services for live the project | SS+SO
|  | Admin will Buy the services for hosting and domain | SO+SR
|  | admin will check the security of website | SS+SO
|  | Admin and editor will live the project for testing on their website | SS+SR
7 | Check the database | DBA will check the database after live the project on server | SS+SR
|  | DBA will fire the queries for various purpose | SS+SO
|  | editor will check the code on server | SR+SO
|  | Admin & editor will check the project for testing on their website | SS+SR+SO
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | SR
|  | Use different applications on the virtual screen | SO
|  | Check the changes made at the virtual screen | SR+SO
|  | Checking if it is working effectively with the laptop and not damaged | SS+SO
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | SO
|  | Prepare all software deliverables | SR
|  | Prepare a hardware & software guide | SO+SR
|  | Prepare a user manual & guide for the users | SR+SO
10 | As a developer I want to give training to USER so that they can interact with the system & use it | Giving information to users about the project | SS
|  | Project demonstration | SS+SO
|  | Project demonstration | SS+SR
|  | Project to be operated by different users | SR+SS
| SS | Shashank Sharma
| SO | Sourav Choudhary
| SR | Shauraya Ranjan
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 20 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <MyCall>
SB2/US1 | Add Editor | SB2/D1/T1 | Designing the GUI | SO | IN PROGRESS
|  | SB2/D1/T2 | Connection with database to fetch the data | SS | COMPLETE
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | SS+SO+SR | IN PROGRESS
SB2/US2 | Register Editor into the application(using mycall email account) | SB2/D2/T1 | Designing of GUI | SO | IN PROGRESS
|  | SB2/D2/T2 | Login Into The System Using Mail Id And Password | SS | IN PROGRESS
|  | SB2/D2/T3 | Prepare Account For All Eligible users | SR | NOT STARTED
|  | SB2/D2/T4 | Access To All Information Of Products | SO | NOT STARTED
|  | SB2/D2/T5 | Manage All Statistics And Data About Product Sale. | SS+SO+SR | NOT STARTED
SB2/US3 | Editor Receiving Confirmation Email | SB2/D3/T1 | Designing of Email(to be send) | SS | IN PROGRESS
|  | SB2/D3/T2 | Send Email via coding using the MyCall email id . | SR | IN PROGRESS
|  | SB2/D3/T3 | Connection with database to update the status in the database. | SO | IN PROGRESS
|  | SB2/D3/T4 | Can Manage the task of Database | SS+SO+SR | IN PROGRESS
SB2/US4 | Register DBA into the application(using MyCall email account) | SB2/D4/T1 | I Can Insert New Records In The Database | SS | IN PROGRESS
|  | SB2/D4/T2 | Validating user input at client level | SO | IN PROGRESS
|  | SB2/D4/T3 | Validating user input at server level | SR | IN PROGRESS
|  | SB2/D4/T4 | Connection with Database to insert the record. | SS | IN PROGRESS
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | SS+SO+SR | IN PROGRESS
SB2/US5 | Admin can work in Database also | SB2/D5/T1 | Login Into The System Using Mail Id And Password | SS | IN PROGRESS
|  | SB2/D5/T2 | Send Email via coding using the MyCall email id . | SO | IN PROGRESS
|  | SB2/D5/T3 | Modify The Account Password | SS | IN PROGRESS
|  | SB2/D5/T4 | Testing of the module on localhost | SS+SO+SR | IN PROGRESS
SB2/US6 | Editor can connect Pages | SB2/D6/T1 | Designing of GUI | SS | IN PROGRESS
|  | SB2/D6/T2 | Validating user Login page | SO | IN PROGRESS
|  | SB2/D6/T3 | Validating user at Signup page | SO | IN PROGRESS
|  | SB2/D6/T4 | Connect login and signup pages | SR | IN PROGRESS
|  | SB2/D6/T5 | Testing of the code | SS+SO+SR | IN PROGRESS
SB2/US7 | Register User into the application | SB2/D7/T1 | Using Login & Signup Pages | SS | IN PROGRESS
|  | SB2/D7/T2 | Using emailid of mycall or any other id | SR | IN PROGRESS
|  | SB2/D7/T3 | Get new userid | SO | IN PROGRESS
|  | SB2/D7/T4 | Data of user with Database to insert the record | SR | IN PROGRESS
|  | SB2/D7/T5 | Get the confirmation Mail From MyCall | SS+SO+SR | IN PROGRESS
SB2/US8 | Admin will manage the work | SB2/D8/T1 | Check the status of work | SO | IN PROGRESS
|  | SB2/D8/T2 | Send Email to employes if he want any any problem to handle it. | SS | IN PROGRESS
|  | SB2/D8/T3 | Check the accuracy of work done | SO | IN PROGRESS
|  | SB2/D8/T4 | Testing of the module on localhost and then on server. | SS+SO+SR | IN PROGRESS

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Add Editor | Designing the GUI | SS+SO
|  | Connection with database to fetch the data | SS+SR
|  | Testing of the module on localhost and then on server. | SO+SR
2 | Register Editor into the application(using mycall email account) | Login Into The System Using Mail Id And Password | SR+SO
|  | Prepare Account For All Eligible users | SO+SR
|  | Access To All Information Of Products | SO
|  | Manage All Statistics And Data About Product Sale. | SR+SO
3 | Editor Receiving Confirmation Email | Designing of Email(to be send) | SS
|  | Send Email via coding using the MyCall email id . | SR+SO
|  | Connection with database to update the status in the database. | SR
|  | Can Manage the task of Database | SO
4 | Register DBA into the application(using MyCall email account | I Can Insert New Records In The Database | SS
|  | Validating user input at client level | SO
|  | Validating user input at server level | SR
|  | Connection with Database to insert the record. | SS+SR+SO
5 | Admin can work in Database also | Login Into The System Using Mail Id And Password | SS+SO
|  | Send Email via coding using the MyCall email id . | SR+SO
|  | Modify The Account Password | SS
|  | Testing of the module on localhost | SO
6 | Editor can connect Pages | Validating user Login page | SR
|  | Connect login and signup pages | SO
|  | Testing of the code | SR
7 | Register User into the application | Using Login & Signup Pages | SS+SO
|  | Using emailid of mycall or any other id | SO
|  | Data of user with Database to insert the record | SR
|  | Get the confirmation Mail From MyCall | SS
8 | Admin will manage the work | Check the status of work | SO
|  | Send Email to employes if he want any any problem to handle it. | SS
|  | Check the accuracy of work done | SR
|  | Testing of the module on localhost and then on server. | SO+SR
| SS | SHASHANK SHARMA
| SO | SOURAV CHOUDHARY
| SR | SHAURAYA RANJAN
Verified By:Rekha Jain Mam
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <MyCall>
SB1/US1 | Design the LogIn Page | SB3/D1/T1 | Design the interface of LogIn page | SS | INPROGRESS
|  | SB3/D1/T2 | Connect the page with Social Media pages | SS | INPROGRESS
|  | SB3/D1/T3 | Design the user dashboard page | SS+SO | INPROGRESS
SB3/US2 | Design the SignUp Page | SB3/D2/T1 | Design the User interfae of SignUp page | SS+SR | INPROGRESS
|  | SB3/D2/T2 | Join the Signup page with Social media | SO+SR | INPROGRESS
|  | SB3/D2/T3 | Connect SignUp page with the Server | SO | INPROGRESS
|  | SB3/D2/T4 | Join UserId with the E-mail | SR | INPROGRESS
|  | SB3/D2/T5 | Design the user dashboard page | SS+SR+SO | INPROGRESS
SB3/US3 | Design Forgot Password Section | SB3/D3/T1 | Design the interface of forgot password page | SO | INPROGRESS
|  | SB3/D3/T2 | Join userid with gmail to verify | SR | INPROGRESS
|  | SB3/D3/T3 | Verify password through gmail | SS | INPROGRESS
|  | SB3/D3/T4 | Inform user about change password | SS | INPROGRESS
SB3/US4 | Design the Home Page | SB3/D4/T1 | Design the interface of Home page | SS+SR | INPROGRESS
|  | SB3/D4/T2 | Design the interface of Contents | SO+SS | INPROGRESS
|  | SB3/D4/T3 | Design Advertisments Section | So+SR | INPROGRESS
|  | SB3/D4/T4 | Make Page Seprately of each Advertisments | SS | INPROGRESS
INPROGRESS
SB3/US5 | Design Advertisments panel | SB3/D5/T1 | Make individual page of each advertisments | SS+SO+SR | INPROGRESS
|  | SB3/D5/T2 | Write all the details of the product | SS | INPROGRESS
|  | SB3/D5/T3 | Take user's feedbacks | SO | INPROGRESS
|  | SB3/D5/T4 | Notify everything to Admin | SR | INPROGRESS
SB3/US6 | Design Product Section | SB3/D6/T1 | Design Search pannel including categorywise | SS+SO+SR | INPROGRESS
|  | SB3/D6/T2 | Search services areawise | SR | INPROGRESS
|  | SB3/D6/T3 | Show locations of services | SR | INPROGRESS
|  | SB3/D6/T4 | Share feedback to admin | SO | INPROGRESS
|  | SB3/D6/T5 | Add Security check section before purchasing | SS+SR | INPROGRESS
SB3/US7 | Live the website | SB3/D7/T1 | Get a domain name for website | SO | INPROGRESS
|  | SB3/D7/T2 | Get a hosting space for website | SO+SS | INPROGRESS
|  | SB3/D7/T3 | Upload the data on the server | SS+SR | INPROGRESS
|  | SB3/D7/T4 | All data is live uploaded and check the connection of pages | SO+SR | INPROGRESS

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Design the LogIn Page | Design the interface of LogIn page | SS
|  | Connect the page with Social Media pages | SS
|  | Design the user dashboard page | SS+SO
2 | Design the SignUp Page | Design the User interfae of SignUp page | SS+SR
|  | Join the Signup page with Social media | SO+SR
|  | Connect SignUp page with the Server | SO+SR
|  | Join UserId with the E-mail | SO
3 | Design Forgot Password Section | Design the interface of forgot password page | SO
|  | Join userid with gmail to verify | SR
|  | Verify password through gmail | SS
4 | Design the Home Page | Design the interface of Home page | SO+SR+SS
|  | Design the interface of Contents | SO+SS
|  | Design Advertisments Section | SO+SR
|  | Make Page Seprately of each Advertisments | SR+SS
| Design Advertisments panel | Make individual page of each advertisments | SS+SO+SR
|  | Write all the details of the product | SS
|  | Take user's feedbacks | SO
|  | Notify everything to Admin | SR
5 | Design Product Section | Design Search pannel including categorywise | SR
|  | Search services areawise | SR
|  | Show locations of services | SO
|  | Share feedback to admin | SR
6 | Live the website | Get a domain name for website | SO
|  | Get a hosting space for website | SS
|  | Upload the data on the server | SR+SS
|  | All data is live uploaded and check the connection of pages | SO+SS
| SS | Shashank Sharma
| SR | Shaurya Ranjan
| SO | Sourav Choudhary
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 80 | 0 | Tasks
2018-10-18 | 80 | 0
2018-10-20 | 110 | 60
2018-10-21 | 90 | 75
2018-10-22 | 120 | 120
2018-10-23 | 50 | 0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <MyCall>
SB4/US1 | Join Database | SB4/D1/T1 | Create Database of Website | SS | INPROGRESS
|  | SB4/D1/T2 | Create Attributes of Databse | SR | PROGRESS
|  | SB4/D1/T3 | Combine database with the website. | SO | INPROGRESS
SB4/US2 | Store in Database | SB4/D2/T1 | Store Signup details in Databse | SR+SS | INPROGRESS
|  | SB4/D2/T2 | Insert Login Details | SO | INPROGRESS
|  | SB4/D2/T3 | Insert Products Details | SS+SO | INPROGRESS
|  | SB4/D2/T4 | Insert Services Data | SO | INPROGRESS
|  | SB4/D2/T5 | Store all details in Database | SR+SO | INPROGRESS
SB4/US3 | Retrive Data | SB4/D3/T1 | Retrive data from Database for logIn | SO+SS | NOT STARTED
|  | SB4/D3/T2 | Show all data of Product or services | SS+SR | INPROGRESS
|  | SB4/D3/T3 | Keep record of all the data with timestrap | SR+SO | INPROGRESS
|  | SB4/D3/T4 | Receive the latest data from the Server | SR | INPROGRESS
SB4/US4 | BackUp/Maintain | SB4/D4/T1 | Take backup of whole database | SS | INPROGRESS
|  | SB4/D4/T2 | Import all data of Website | SR | INPROGRESS
|  | SB4/D4/T3 | Keep an Offline SQL backup file | SO | INPROGRESS
|  | SB4/D4/T4 | Update the backup file | SO | INPROGRESS
|  | SB4/D4/T5 | Maintain the new updates | SS | INPROGRESS
SB4/US5 | Testing | SB4/D5/T1 | Test the working of Website | SS | INPROGRESS
|  | SB4/D5/T2 | Connection of webpages | SO | INPROGRESS
|  | SB4/D5/T3 | Working of each fields | SR | INPROGRESS
|  | SB4/D5/T4 | Insert and Retrive of all Data in Webpages | SR+SO | INPROGRESS

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Join Database | Create Database of Website | SS+SO
|  | Create Attributes of Databse | SR
|  | Combine database with the website. | SR+SO
2 | Store in Database | Store Signup details in Databse | SS+SR
|  | Insert Login Details | SS+SO
|  | Insert Products Details | SO
|  | Insert Services Data | SO
3 | Retrive Data | Retrive data from Database for logIn | SS
|  | Show all data of Product or services | SR
|  | Keep record of all the data with timestrap | SR+SO
|  | Receive the latest data from the Server | SS
4 | BackUp/Maintain | Take backup of whole database | SS
|  | Import all data of Website | SR+SO
|  | Keep an Offline SQL backup file | SO+SS
|  | Update the backup file | SO
5 | Testing | Test the working of Website | SS+SR+SO
|  | Connection of webpages | SS
|  | Working of each fields | SR
|  | Insert and Retrive of all Data in Webpages | SO
| SS | Shashank Sharma
| SR | Shaurya Ranjan
| SO | Sourav Choudhary
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 100 | 80
2019-01-13 | 125 | 90
2019-01-14 | 150 | 70
2019-01-15 | 0 | 0
0
Days